## Case Study Data
Project ID | Project Name | Project Manager | Area | Project Kick-Off Forecast Date | Project Kick-Off Actual Date | Contruction Start Forecasted | Construction Start Actual Date | Project Close Date Forecasted | Project Close Actual Date | Jan Budget Forecast | Feb Budget Forecast | Mar Budget Forecast | April Budget Forecast | May Budget Forecast | June Budget Forecast | July Budget Forecast | Aug Budget Forecast | Sept Budget Forecast | Oct Budget Forecast | Nov Budget Forecast | Dec Budget Forecast | Jan Budget Actuals | Feb Budget Actuals | Mar Budget Actuals | April Budget Actuals | May Budget Actuals | June Budget Actuals | July Budget Actuals | Aug Budget Actuals | Sept Budget Actuals | Oct Budget Actuals | Nov Budget Actuals | Dec Budget Actuals | Project Risk
PRJ001 | Chatanooga Cable Press 2 | Joe | North | 2022-01-28 | 2022-01-28 | 2022-05-22 | 2022-05-22 | 2022-10-22 | 2022-10-22 | 166786 | 96408 | 214847 | 218094 | 19300 | 25599 | 114017 | 252786 | 106904 | 34742 | 104854 | 134586 | 372583 | 340451 | 257581 | 421084 | 221938 | 59948 | 383961 | 550600 | 375346 | 262602 | 320650 | 186871 | Medium
PRJ002 | Oroville Breaker Select | Dan | North | 2022-01-15 | 2022-01-15 | 2022-05-11 | 2022-05-11 | 2022-10-27 | 2022-12-21 | 65045 | 28607 | 257636 | 197939 | 65626 | 92677 | 161106 | 15282 | 36348 | 69948 | 30969 | 68788 | 166924 | 163617 | 423984 | 360526 | 177072 | 155851 | 407152 | 32849 | 119662 | 90442 | 48325 | 132713 | Low
PRJ003 | Lake Shasta T-Line | Emilia | North | 2022-01-18 | 2022-02-10 | 2022-05-16 | 2022-05-24 | 2022-10-31 | 2022-11-08 | 240595 | 83106 | 32810 | 274020 | 62636 | 160904 | 285900 | 42204 | 29839 | 292013 | 77028 | 242407 | 365291 | 118047 | 265843 | 359454 | 212269 | 384859 | 336540 | 269265 | 86363 | 503240 | 279684 | 501469 | Low
PRJ004 | Los Banos Substation | Rakesh | South | 2022-01-25 | 2022-02-17 | 2022-06-12 | 2022-06-12 | 2022-10-24 | 2022-11-25 | 225370 | 152254 | 134335 | 217808 | 65992 | 175181 | 180676 | 69508 | 21922 | 49868 | 159971 | 38448 | 260986 | 309306 | 386245 | 267329 | 217430 | 380828 | 239726 | 310925 | 54573 | 339767 | 443964 | 43487 | Low
PRJ005 | Oakland Substation S | Susanna | Central | 2022-02-05 | 2022-02-28 | 2022-07-31 | 2022-07-31 | 2022-10-19 | 2022-10-19 | 179565 | 291159 | 101952 | 69912 | 158577 | 167821 | 98886 | 75458 | 177449 | 157222 | 230871 | 189613 | 250397 | 493052 | 128819 | 278646 | 178855 | 462955 | 159416 | 285514 | 317470 | 273294 | 420190 | 418535 | High
PRJ006 | San Francisco Center Cable Upgrade | Sean | Central | 2022-02-01 | 2022-02-09 | 2022-06-16 | 2022-06-07 | 2022-11-03 | 2022-11-03 | 178963 | 281139 | 295937 | 116784 | 167801 | 102075 | 180437 | 95957 | 189835 | 217416 | 137048 | 261621 | 425111 | 454943 | 471123 | 317461 | 295330 | 254894 | 456654 | 262031 | 238025 | 335934 | 284110 | 432267 | Medium
PRJ007 | Napa Conductor Upgrade | Ben | North | 2022-01-10 | 2022-03-09 | 2022-05-19 | 2022-08-17 | 2022-10-31 | 2022-12-14 | 137399 | 118084 | 147676 | 14275 | 98615 | 103234 | 133122 | 30455 | 245044 | 250342 | 124749 | 71947 | 181913 | 278989 | 270149 | 99869 | 207920 | 200764 | 390624 | 306551 | 532555 | 305826 | 124704 | 158335 | Medium
PRJ008 | Bay Bridge pole upgrade | Ericka | Central | 2022-02-09 | 2022-02-09 | 2022-05-13 | 2022-05-13 | 2022-12-08 | 2023-02-16 | 238469 | 227255 | 131561 | 256966 | 233676 | 102463 | 137607 | 185320 | 225561 | 60772 | 55424 | 251379 | 373948 | 293251 | 413592 | 350403 | 287951 | 236106 | 433778 | 444788 | 398741 | 273232 | 188920 | 269572 | Medium
PRJ009 | Santa Rosa TL2 Upgrade | Rachel | North | 2022-02-01 | 2022-01-25 | 2022-08-05 | 2022-08-05 | 2022-12-15 | 2023-01-16 | 227172 | 177406 | 283063 | 57638 | 44697 | 122039 | 246411 | 200602 | 15716 | 83362 | 216553 | 249858 | 451788 | 381318 | 443338 | 339724 | 324469 | 374672 | 340066 | 409172 | 40984 | 200664 | 398298 | 257573 | High
PRJ010 | Stockton Set 34 | krista | North | 2022-02-07 | 2022-02-07 | 2022-05-21 | 2022-05-21 | 2022-10-23 | 2022-10-23 | 149108 | 121189 | 239947 | 46226 | 139795 | 99726 | 192128 | 231213 | 292053 | 102998 | 160278 | 76802 | 306349 | 208890 | 484469 | 112341 | 184701 | 230055 | 351777 | 490329 | 452059 | 339338 | 335151 | 335303 | High
PRJ011 | Marin County Insultaror change 3 | Beth | Central | 2022-01-10 | 2022-01-10 | 2022-07-06 | 2022-07-06 | 2022-11-17 | 2022-11-17 | 48244 | 222987 | 116822 | 128633 | 146444 | 290151 | 35191 | 78358 | 97775 | 102833 | 15682 | 291169 | 308254 | 336914 | 323616 | 145396 | 230346 | 385710 | 128787 | 216165 | 205695 | 401062 | 202919 | 396890 | Medium
PRJ012 | Hayward t-Line Sub | Sahil | Central | 2022-01-28 | 2022-01-28 | 2022-04-08 | 2022-04-08 | 2022-11-20 | 2022-11-20 | 248080 | 266838 | 237375 | 255336 | 183280 | 217675 | 19056 | 255271 | 272739 | 149235 | 78825 | 101416 | 535264 | 489273 | 383681 | 373618 | 334793 | 366078 | 211156 | 345478 | 408859 | 356784 | 345804 | 275753 | Medium
PRJ013 | SLO T-Sub 6 | Julio | South | 2022-01-07 | 2022-01-07 | 2022-04-09 | 2022-04-09 | 2022-12-04 | 2022-12-04 | 224636 | 276481 | 19364 | 179365 | 20994 | 170775 | 259716 | 244966 | 181659 | 226100 | 36971 | 277736 | 465440 | 348655 | 54033 | 290973 | 263588 | 425208 | 277091 | 516764 | 411714 | 523350 | 83947 | 296754 | Medium
PRJ014 | Pismo Tower Upgrade | Kavita | South | 2022-02-08 | 2022-02-08 | 2022-08-03 | 2022-08-03 | 2022-12-05 | 2022-12-05 | 257689 | 154869 | 265540 | 136369 | 287233 | 91718 | 121253 | 103148 | 211181 | 149902 | 46997 | 113871 | 539528 | 392998 | 367019 | 154253 | 453756 | 169439 | 356205 | 358756 | 372050 | 333879 | 281132 | 359009 | Medium
PRJ015 | Fresno Breaker Upgrade | Barbara | South | 2022-01-01 | 2022-03-31 | 2022-07-25 | 2022-10-21 | 2022-11-05 | 2022-11-16 | 247956 | 249648 | 285804 | 66564 | 248277 | 176021 | 292568 | 181268 | 113979 | 281417 | 112173 | 297172 | 485666 | 472329 | 514732 | 238363 | 415621 | 211065 | 578423 | 441914 | 210764 | 576084 | 173946 | 472581 | Low
PRJ016 | Rocklin Pole Program exchange | Carter | North | 2022-01-05 | 2022-01-26 | 2022-08-04 | 2022-08-13 | 2022-11-01 | 2022-11-01 | 66616 | 113265 | 167646 | 263876 | 294897 | 154131 | 140514 | 81441 | 297320 | 232133 | 270922 | 182801 | 129827 | 251575 | 332977 | 295304 | 337924 | 305664 | 314421 | 224663 | 312485 | 442288 | 376080 | 320971 | Low
PRJ017 | Modesto Conductor Repair | Jackie | South | 2022-01-13 | 2022-01-13 | 2022-05-18 | 2022-05-18 | 2022-12-09 | 2022-12-09 | 168400 | 38632 | 46086 | 97075 | 198722 | 159150 | 284989 | 33084 | 31134 | 188040 | 116920 | 170162 | 267913 | 150864 | 337140 | 380640 | 260938 | 183471 | 378947 | 290850 | 273331 | 199687 | 213285 | 211534 | Low
PRJ018 | Carmel Tline-D Sub | Huan | South | 2022-01-05 | 2022-01-05 | 2022-08-05 | 2022-08-05 | 2022-10-05 | 2023-01-13 | 113243 | 63826 | 130950 | 191964 | 34710 | 259654 | 260530 | 106980 | 10592 | 253491 | 108921 | 191175 | 164908 | 260318 | 154787 | 237825 | 270004 | 352011 | 540808 | 292988 | 263507 | 453192 | 173388 | 222949 | Low
PRJ019 | Moss Landing Power Gen | Kyle | South | 2022-02-12 | 2022-02-12 | 2022-06-12 | 2022-06-12 | 2022-12-15 | 2023-01-14 | 290629 | 270509 | 232716 | 62987 | 288111 | 129880 | 256453 | 22007 | 27364 | 65996 | 142774 | 81851 | 432643 | 534169 | 516067 | 340674 | 546117 | 425997 | 436421 | 136354 | 226424 | 343096 | 387599 | 253870 | High
PRJ020 | Sonoma D-Sub | Dylan | North | 2022-02-14 | 2022-02-22 | 2022-06-02 | 2022-08-11 | 2022-10-31 | 2022-10-31 | 44028 | 191176 | 94545 | 42584 | 103600 | 282354 | 189996 | 45488 | 269285 | 49575 | 185016 | 81811 | 191870 | 459375 | 159350 | 97903 | 246514 | 504254 | 252907 | 306757 | 289940 | 62324 | 263568 | 81108 | High